## Progress
TATA PROJECTS LIMITED
PROJECT NAME: PIPING PROJECT (340092) | [9 empty] | Progress as on | 2021-10-23
DAILY PROGRESS REPORT | [9 empty] | Report Date | 2021-10-23
11550
S.No | Description | Unit | Total Scope | Progress upto previous month | Planned for the month | Progress For the Month |  |  | Upto date progress | Balance | Remarks
[6 empty] | Till Yesterday | Today | Cumm. | [5 empty] | Till
A | Supply
1 | Pipes( Receiving at site) | Mtr | 107231 | 95680 | 5000 | 0 |  | 0 | 95680 | 11550
| Blasting | Mtr | 75182 | 49495 | 6000 | 3066.93 |  | 3066.93 | 52561.93 | 22620.07 |  | -4730.55 | -4730.55 | 16-Sep
| Painting (Primer) | Mtr | 75182 | 49495 | 6000 | 3066.93 |  | 3066.93 | 52561.93 | 22620.07 |  |  |  | 16-Sep
2 | Flanges | Nos | 5821 | 21323 | 300 | 0 |  | 0 | 21323 | 75709
3 | Fittings | Nos | 16737 | 14433 | 200 | 0 |  | 0 | 14433 | 2304
4 | Strainers | Nos | 30 | 0 |  | 0 |  | 0 | 0 | 30
5 | Gaskets | Nos | 3993 | 0 |  | 0 |  | 0 | 0 | 3993
6 | Fasteners | Nos | 22544 | 0 |  | 0 |  | 0 | 0 | 22544
7 | Valves | Nos | 2611 | 0 | 350 | 0 |  | 0 | 0 | 2611
B | Mechanical
1 | Fabrication of Pipe Specials | Nos | 1 | 0 |  | 0 |  | 0 | 0 | 1 | Pipe Sleeper : Precasted = 2436 nos Shifted = 1282 nos Placed = 1282 nos Backfilled = 1020 nos
2 | CS-Fabrication of Pipe (Butt Weld) Thk<=10 MM | ID | 123470 | 0 |  | 0 |  | 0 | 0 | 123470 |  | -11066
| Fitup | ID | 123470 | 22022 | 10000 | 7574 | 78 | 7652 | 29674 | 93796 |  |  |  | 23-Sep
| Welding | ID | 123470 | 22022 | 10000 | 7422.5 | 274 | 7696.5 | 29718.5 | 93751.5 |  |  |  | 23-Sep
3 | CS-Fabrication of Pipe (Fillet Weld) Thk<=10 MM | ID | 28140 | 57 |  | 0 |  | 0 | 57 | 28083
4 | Erection (Other than Spools) : CS | IM | 604060 | 0 |  | 0 |  | 0 | 0 | 604060
| Placing | IM | 489572 | 146598 | 40000 | 35441.88 | 1728 | 37169.88 | 183767.88 | 305804.12 |  |  |  | 21-Sep
| Alignment & Hydrotest | IM | 604060 | 6000 |  |  |  |  | 6000 | 598060
5 | SS-Fabrication of Pipe (Butt Weld) Thk<=10 MM | ID | 5100 | 0 |  | 0 |  | 0 | 0 | 5100
6 | SS-Fabrication of Pipe (Fillet Weld) Thk<=10 MM | ID | 5430 | 0 |  | 0 |  | 0 | 0 | 5430
7 | Erection (Other than Spools) : SS | IM | 22865 | 0 |  | 0 |  | 0 | 0 | 22865
8 | Carbon Steel Galvanized | Mtr | 35010 | 486 |  | 0 |  | 0 | 486 | 34524
9 | Rubber Lined Piping | Mtr | 2000 | 0 |  | 0 |  | 0 | 0 | 2000
10 | Valves - Flanged / Wafer Valves | Nos | 1167 | 0 |  | 0 |  | 0 | 0 | 1167
11 | Valves - Control Valves | Nos | 98 | 0 |  | 0 |  | 0 | 0 | 98
12 | Valves - Rubber Lined Valves | Nos | 39 | 0 |  | 0 |  | 0 | 0 | 39
13 | Valves - Press Relief / Safety Valves | Nos | 79 | 0 |  | 0 |  | 0 | 0 | 79
14 | Bolt Tensioning | Nos | 6 | 0 |  | 0 |  | 0 | 0 | 6
15 | Reinforcing Pipes for Pads | Nos | 29 | 0 |  | 0 |  | 0 | 0 | 29
16 | Radiography - For Joints THK. <= 8MM (FOR CS than Class IV ) | Nos | 1400 | 78 |  |  |  |  | 78 | 1322 |  |  |  | 24-Sep
17 | Radiography - For Joints THK. <= 8MM (FOR CS as per Class IV ) | Nos | 262 | 0 |  | 0 |  | 0 | 0 | 262 |  |  |  | 24-Sep
18 | Radiography - For Joints above THK. 8MM | Nos | 1725 | 26 | 20 | 0 |  | 0 | 26 | 1699 |  |  |  | 24-Sep
19 | DYE Penetration / Magnetic Particle test | Inches | 3686 | 188.4 | 200 | 0 |  | 0 | 188.4 | 3497.6 |  |  |  | 24-Sep
20 | CS Strucutural Steel- Supports | MT | 9 | 9 |  | 0 |  | 0 | 9 | 0 |  |  |  | 24-Sep
21 | SS Structural Steel- Supports | MT | 2 | 0 |  | 0 |  | 0 | 0 | 2
22 | Dummy Pipe Supports for CS | MT | 17 | 0 |  | 0 |  | 0 | 0 | 17
23 | Dummy Pipe Supports for SS | MT | 3 | 0 |  | 0 |  | 0 | 0 | 3
24 | Stress Relieving | Nos | 347 | 0 |  | 0 |  | 0 | 0 | 347
25 | Chemical Cleaning / Pickling | Mtr | 10440 | 0 |  | 0 |  | 0 | 0 | 10440
26 | Modification / Extra Works - CS Pipe (IBR/NON-IBR) | ID | 9140 | 0 |  | 0 |  | 0 | 0 | 9140
27 | Modification / Extra Works - SS Pipe (IBR/NON-IBR) | ID | 620 | 0 |  | 0 |  | 0 | 0 | 620
28 | Removal of Erected Piping (Above Ground) - CS | IM | 12565 | 0 |  | 0 |  | 0 | 0 | 12565
29 | Removal of Erected Piping (Above Ground) - SS | IM | 460 | 0 |  | 0 |  | 0 | 0 | 460
30 | Dismantling & Erection of Re-erection of valves - Control Valves | Nos | 98 | 0 |  | 0 |  | 0 | 0 | 98
31 | Dismantling & Erection of Re-erection of valves - Press. Relief/Safety Valves | Nos | 79 | 0 |  | 0 |  | 0 | 0 | 79
32 | Opening & Boxing Up of Piping / Equipment Flanges & Blinding | Nos | 776 | 0 |  | 0 |  | 0 | 0 | 776
33 | Manpower assistance for Pre-commissioning activities | MD | 4680 | 0 |  | 0 |  | 0 | 0 | 4680
34 | Cleaning of Strainers / Filters | Nos | 122 | 0 |  | 0 |  | 0 | 0 | 122
35 | Fabrication of Tail Blinds | Nos | 208 | 0 |  | 0 |  | 0 | 0 | 208
36 | Supply and Application of Paints & Primers (-14 to 80 deg C)- Valves | Nos | 641 | 0 |  | 0 |  | 0 | 0 | 641
37 | Supply and Application of Paints & Primers (-14 to 80 deg C)- Valves | Nos | 213 | 0 |  | 0 |  | 0 | 0 | 213
C | Civil and Architechtural Works
1 | Plain Reinforcement Concrete - PCC M20 | Cum | 20 | 0 |  | 0 |  | 0 | 0 | 20
2 | Supply, Fabrication & Shop primer of Structural Steel | MT | 4400 | 3383 | 400 | 0 |  | 0 | 3383 | 1017 |  |  |  | o.k | 9.4 | 40.2 | -12
3 | Erection of Structural Steel |  |  | 0 |  | 0 |  | 0 | 0 | 0 |  |  | -35.6 | -65.1
| Placement | MT | 4400 | 2160.1 | 500 | 179.6 | 10 | 189.6 | 2349.7 | 2050.3 |  | -594.6 |  | o.k. | 87.2
| Alignment | MT | 4400 | 1457.8 | 500 | 242.7 | 7 | 249.7 | 1707.5 | 2692.5 |  | -418 |  | o.k. | -172.6
| Welding | MT | 4400 | 1797.7 | 500 | 564.7 | 12 | 576.7 | 2374.4 | 2025.6 |  | -576.7 |  | o.k. | -94.2
4 | Painting (Final & Touch-Ups) - NON FIM | MT | 4400 | 3181 | 300 | 0 |  | 0 | 3181 | 1219 |  |  |  | 24-Sep
5 | Supply, Fabrication & Erection of MS chequered plates | MT | 2 | 0 |  | 0 |  | 0 | 0 | 2 |  | -28.1 | -29.3
6 | Supply of Fabricated Grating material | MT | 250 | 145 | 100 |  |  |  | 145 | 105 |  | -25 |  | 24-Sep
7 | Erection of Electroforged Grating | MT | 250 | 7 |  | 0 |  | 0 | 7 | 243 |  |  |  | 24-Sep | 7
8 | Supply, Fabrication & Erection of Cold Forge light Gauge Steel | MT | 0.05 | 0 |  | 0 |  | 0 | 0 | 0.05
9 | Medium Duty Fasterners | Each | 20 | 0 |  | 0 |  | 0 | 0 | 20
10 | Supply of Hand rail material | Mtr | 4400 | 0 | 1500 |  |  |  | 0 | 4400
11 | Fabrication, installation and Painting of Horz. Handrail 1000mm | Mtr | 4400 | 0 |  | 0 |  | 0 | 0 | 4400
12 | Supply and Fixing Mechanical Anchor Fasteners | Each | 30 | 0 |  | 0 |  | 0 | 0 | 30
13 | Supply and Fixing Bolts in equipment saddle. | MT | 1 | 0 |  | 0 |  | 0 | 0 | 1
14 | Demolishing & Dismantling - RCC | Cum | 10 | 0 |  | 0 |  | 0 | 0 | 10
15 | Dismantling bolted/rivetted/welded STRUCTURAL STEEL WORK | MT | 2 | 0 |  | 0 |  | 0 | 0 | 2
16 | Supply & Laying of MS galvanised pipes | Mtr | 8260 | 0 |  | 0 |  | 0 | 0 | 8260
17 | Mis.Civil & Structural Work for UG Piping | Cum | 3090 | 0 |  | 0 |  | 0 | 0 | 3090
18 | Supply and Installation of combined Safety shower and eye wash unit | Each | 5 | 0 |  | 0 |  | 0 | 0 | 5
19 | Supply & Installation of Fire Fighting Equipments | Nos | 1005 | 0 |  | 0 |  | 0 | 0 | 1005
20 | Radiographic Inspection - For Joints Thk<=8mm other than class IV | Nos | 5 | 0 |  | 0 |  | 0 | 0 | 5
21 | Radiographic Inspection - For Joints Thk >8mm | Nos | 44 | 0 |  | 0 |  | 0 | 0 | 44
22 | Supply / Installation of valve assembly | Nos | 21 | 0 |  | 0 |  | 0 | 0 | 21
23 | MV Spray System on Tanks ( Supply and Installation ) | Each | 2 | 0 |  | 0 |  | 0 | 0 | 2
24 | Supply / Laying UG GI PIPE | Mtr | 670 | 0 |  | 0 |  | 0 | 0 | 670
25 | Laying / Joining of Fire Water pipes | Mtr | 1950 | 0 |  | 0 |  | 0 | 0 | 1950
26 | Auto Actuated HV Spray System on transformers ( Supply & Installation ) | LS | 6 | 0 |  | 0 |  | 0 | 0 | 6
27 | MV Spray System on Cable Cellar ( Supply & Installation ) | LS | 4 | 0 |  | 0 |  | 0 | 0 | 4
28 | Supply & Installation for Hydro-Pneumatic System for FW network | LS | 1 | 0 |  | 0 |  | 0 | 0 | 1
29 | Excavation Work IN ROAD EMBANKMENT | Cum | 715 | 0 |  | 0 |  | 0 | 0 | 715
30 | Laying /Joining CS PIPES IN RCC TRENCH DIA 300 | Mtr | 1590 | 0 |  | 0 |  | 0 | 0 | 1590
D | Equipment
1 | Fuel Dispensing Unit | Nos | 2 | 0 |  | 0 |  | 0 | 0 | 2
2a | Breathing Air Bullet- Supply | Nos | 16 | 15 | 1 | 0 |  | 0 | 15 | 1
2b | Breathing Air Bullet- Erection | Nos | 16 | 2 |  | 4 |  | 4 | 6 | 10 | Civil Foundations Required for Erection |  |  | 24-Sep | 3 | 1
3 | MS Tank - 20 KL | Nos | 2 | 0 |  | 0 |  | 0 | 0 | 2
4 | Cracked Ammonia Unit | LOT | 3 | 0 |  | 0 |  | 0 | 0 | 3
5 | Breathing Air Compressors | Nos | 3 | 3 |  | 0 |  | 0 | 3 | 0 |  |  |  | 24-Sep
6 | Supply of Pumps with electrical motor | Nos | 9 | 0 |  | 0 |  | 0 | 0 | 9
7 | Diesel Engine Driven Horizontal Certifugal Fire Water Pump | Nos | 2 | 0 |  | 0 |  | 0 | 0 | 2
8 | Diesel Storage Fixed Roof Tanks - | Nos | 2 | 0 |  | 0 |  | 0 | 0 | 2
Constraint:
Due to Frequent lockdown the dispatch of Pipe Rack Structures from factories are being delayed .

## Manpower & Machinery
TATA PROJECT LIMITED
DAILY MANPOWER & MACHINERY REPORT
PROJECT: PIPING PROJECT (340092) |  |  |  | Progress as on |  |  | 2021-10-23
|  |  |  | Report Date |  |  | 2021-10-23
Sr. No. | Category | TPL | Sub-Contractor |  |  |  | Total
|  |  | Artson - Pipe Rack Structure | Lansh - Piping work | SLG - Grating & Handrail work. | ICCPL - Fire Protection Work
Staff
1 | RCM | 1 | 1 |  |  |  | 2
2 | Site Incharge | 1 | 2 | 1 |  |  | 4
3 | Planning Manager/ Engineer | 1 | 1 | 3 |  |  | 5
4 | Document Controller | [5 empty] | 0
5 | Structural Engineer/Manager | 2 | 3 |  |  |  | 5
6 | Structural Supervisor |  | 8 |  |  |  | 8
7 | Piping Engineer/Manager | 2 |  | 5 |  |  | 7
8 | Piping Supervisor |  |  | 0 |  |  | 0
9 | Equipment Engineer |  |  | 0 |  |  | 0
10 | Equipment Supervisor | [5 empty] | 0
11 | Erection Foreman | 1 | 1 |  |  |  | 2
12 | Electrician | 1 |  | 0 |  |  | 1
13 | SCM | 1 |  |  |  |  | 1
14 | Stores Incharge | 1 |  | 1 |  |  | 2
15 | Stores Assistant | 1 |  | 1 |  |  | 2
16 | HR & Admin |  | 1 | 1 |  |  | 2
17 | EHS Incharge | 1 |  |  |  |  | 1
18 | EHS Officer | 1 | 1 | 1 |  |  | 3
19 | EHS Steward | [5 empty] | 0
20 | Quality Engineer/Manager | 2 | 1 | 1 |  |  | 4
21 | Quality Supervisor |  | 8 |  |  |  | 8
22 | Surveyor | 1 | 0 |  |  |  | 1
23 | Facility Engineer | [5 empty] | 0
| TOTAL | 17 | 27 | 14 |  |  | 58
Workmen
24 | Mechanic | [5 empty] | 0
25 | Crane Operator |  |  | 1 |  |  | 1
26 | Hydra Operator |  | 4 | 2 |  |  | 6
27 | Trailor Operator |  |  | 1 |  |  | 1
28 | scafolding |  |  | 7 |  |  | 7
29 | Fitter |  | 18 | 9 |  |  | 27
30 | Welder |  | 21 | 19 |  |  | 40
31 | Rigger |  | 27 | 30 | 3 | 2 | 62
32 | Helper |  | 25 | 31 | 1 | 2 | 59
33 | Khalasi |  |  | 26 |  | 1 | 27
34 | Grinder |  | 9 | 10 |  |  | 19
35 | Gas Cutter |  |  | 1 |  |  | 1
36 | Electrician |  | 2 | 1 |  |  | 3
38 | Supervisor-Blasting |  |  | 1 | 1 | 2 | 4
39 | Blaster |  |  | 2 |  |  | 2
40 | Painter |  | 5 | 2 |  |  | 7
41 | Helper-Blasting |  |  | 6 |  |  | 6
42 | RT Technician | [5 empty] | 0
| TOTAL | 0 | 111 | 149 | 5 | 7 | 272
T & P Status
1 | Hydra | 1 | 5 | 2 | 0 | 0 | 8
2 | Trailer | 0 | 1 | 1 | 0 | 0 | 2
3 | Manlifter | 1 | 1 | 0 | 0 | 0 | 2
4 | Crane (30T & 50T) | 1 | 1 | 0 | 0 | 0 | 2
5 | DG Set (44kva, 62kva & 120kva) | 3 | 0 | 0 | 0 | 0 | 3

## Pipe Rack Status
Pipe Rack Tracking as on 23-Oct-2021
Sl. No. | Area | Type of footings | Number of Footings | Number of footings casted | Number of footings balance | Number of footings under hold | Total number of design Drawings | Number of drawings cleared | Number of drawings pending | Structure Tonnage as per design drawing | Priority | Any other Constraint (foundation,drawing,hold information) | Material (Str) received at site | Material (Str) erected Till now | Working Status
1 | Area-1 | Foundation | 31 | 21 | 10 | 0 | 6 | 6 | 0 | 223 | Priority-3 |  | 100.1 | 69.2 | ERECTION OF TIE MEMBERS
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Area-2 | Foundation | 25 | 11 | 14 | 0 | 5 | 5 | 0 | 134 | Priority-3 |  | 128 | 27.2 | ERECTION OF PORTALS
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Area-3 | Foundation | 30 | 0 | 30 | 0 | 5 | 5 | 0 | 147 | Priority-3 |  | 151.7 | 44.2
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Area-4 | Foundation | 33 | 17 | 16 | 0 | 6 | 6 | 0 | 199 | Priority-3 |  | 180.7 | 43.4 | ERECTION OF PORTALS & ERECTION OF PORTALS
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Area-5 | Foundation | 33 | 33 | 0 | 0 | 4 | 4 | 0 | 123 | Priority-2 |  | 122.9 | 86 | ERECTION OF TIE MEMBERS
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Area-6 | Foundation | 43 | 39 | 4 | 0 | 7 | 7 | 0 | 237 | Priority-1B |  | 318.7 | 235.2 | ERECTION OF GALLERY
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Area-7 | Foundation | 25 | 24 | 1 | 0 | 6 | 6 | 0 | 154 | Priority-1A | Need Foundation handover from Plants & Non-Plants | 160.6 | 160.6 | ERECTION OF CABLE DUCTS
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Area-8 | Foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
|  | T-Sleeper | 33 | 0 | 33 | 0 | 1 | 0 | 0
9 | Area-9 | Foundation | 26 | 26 | 0 | 0 | 9 | 9 | 0 | 311 | Priority-1A | Need Foundation handover from Plants & Non-Plants | 285 | 282.2 | erection of tie MEMBERS
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Area-10 | Foundation | 43 | 43 | 0 | 0 | 5 | 5 | 0 | 245 | Priority-1A |  | 264.6 | 261.2 | erection of PORTALS
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Area-11 | Foundation | 24 | 24 | 0 | 0 | 8 | 8 | 0 | 231 | Priority-1A |  | 172.4 | 172.4 | erection of tie MEMBERS
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Area-12 | Foundation | 22 | 22 | 0 | 0 | 5 | 5 | 0 | 131 | Priority-1B |  | 134.3 | 125.9 | erection of beam and bracing
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Area-13 | Foundation | 23 | 19 | 4 | 0 | 6 | 6 | 0 | 155 | Priority-2 |  | 160.1 | 122.6 | FIT-UP OF GALLERY
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Area-14 | Foundation | 29 | 0 | 29 | 0 | 9 | 8 | 1 | 315 | Priority-3 |  | 108
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Area-15 | Foundation | 40 | 35 | 5 | 0 | 10 | 10 | 0 | 332 | Priority-2 | 7 Foundations under hold | 237.6 | 193.5 | ERECTION OF BRIDGE COLUMN (BOX-UP)
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Area-16 | Foundation | 52 | 26 | 26 | 0 | 9 | 8 | 1 | 286 | Priority-1C | 7 Foundations under hold | 287.6 | 110.3 | WELDING & ASSEMBLY OF PORTALS/ERECTION OF PORTALS
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Area-17 | Foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T-Sleeper | 31 | 0 | 31 | 0 | 1 | 0 | 0
18 | Area-18 | Foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T-Sleeper | 20 | 0 | 20 | 0 | 1 | 0 | 0
19 | Area-19 | Foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T-Sleeper | 61 | 0 | 61 | 0 | 1 | 0 | 0
20 | Area-20 | Foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T-Sleeper | 29 | 0 | 29 | 0 | 1 | 0 | 0
21 | Area-21 | Foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T-Sleeper | 150 | 0 | 150 | 0 | 1 | 0 | 0
22 | Area-22 | Foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T-Sleeper | 27 | 0 | 27 | 0 | 1 | 0 | 0
23 | Area-23 | Foundation | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Area-24 | Foundation | 33 | 24 | 9 | 0 | 5 | 5 | 0 | 147 | Priority-2 |  | 190.7 | 50.2
|  | T-Sleeper | 61 | 0 | 61 | 0 | 1 | 0 | 0
25 | Area-25 | Foundation | 97 | 14 | 83 | 0 | 8 | 7 | 1 | 330 | Priority-2 |  | 342.5 | 122.7
|  | T-Sleeper | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | Foundation | 609 | 378 | 231 | 0 | 113 | 110 | 3 | 3700 |  |  | 3345.5 | 2106.8
|  | T-Sleeper | 412 | 0 | 412 | 0 | 8 | 0 | 0
26 | Additional(Melt Shop) | Intra Plant pipe cum cable tray support |  |  |  |  | 1 | 1 | 0 | 90 | Priority-1C |  | 99.6 | 53.3 | FIT-UP & WELDING OF MEMBERS
Remarks: |  | 1. On T-Sleeper piping & Intra plant piping, Wherever the underground road/ramp crossing occurs - hume pipes/RCC trenches/pipe culverts front required as applicable in drawings from Plants & Non-Plants.

## Pipe Rack Constraint
List of Super Structural Drawings pending from EIL/NFC - As on date 10-Oct-2021
Pipe Rack Structure - GAD/Design Drawing
Sl.No. | Area No. | Drawing No. | Observations | Remarks | STATUS as on date
1 | Area-1 | A367-040-16-48-00701 | Area 1 FDN drg 00701 issued on 25.08.20 by EIL, but drg not received from NFC. |  | Resolved, Drg. Received on 16-12-2020
2 |  | A367-040-81-41-06704; R-2 | Descrepancy in the TOG elevation of Grid 1-19/38 & Grid 20/38, Because the Tier-1 from 15-01 (A367-040-81-41-06774; R-1) is fouling wih the concrete column of Grid 1-19/38 & Grid 1-20/38. | Area-1 fabricated pipe rack structures are started to receive at site. | Resolved, on date 10-12-2020
3 | Area-15 | A367-040-81-41-06774; R-1 |  |  | Resolved, on date 10-12-2020
4 |  | A367-040-16-48-00771 |  |  | Pipe Rack & Pipe Bridge - 7 Foundation HOLD released by NFC. Foundations casting pending.
5 |  | A367-040-16-48-00772
6 |  | A367-040-16-48-00773
7 |  | A367-040-81-41-06774
8 |  | A367-040-81-41-06784
4 | Area-4 | A367-040-16-48-00716; R-3 | In this foundation layout drawing, the grid 4-04 & 4-05 is marked as HOLD, but in super structure drawing the same is not marked, need clarification. | Already replied this thing on receipt of the drawing. | Resolved, Drg. Received on 16-12-2020
5 | Area-6 | A367-040-81-41-06732; R-2 | Mismatch of connecting beam (Tier-1) level to pipe bridge. Same is marked on the RFI drawing shared through mail. |  | Clarified on 29-12-2020 & found O.K. w.r.t. the latest revision
6 |  | A367-040-16-48-00726; R-3 | Grid 6-41 & 6-42 is kept under hold by EIL for the purpose of some changes in piping GAD may affect this grid. | Recent comment by EIL. | Resolved
7 | Area-14 | A367-040-16-48-00766 | Due to change in Road location for Extrusion Bldg, Client (Civil Dept) may revise the foundation layout. Due to this reason detail engg not done. |  | Resolved
8 |  | A367-040-16-48-00767 |  |  | Resolved
9 |  | A367-040-16-48-00768 |  |  | Resolved
10 |  | A367-040-81-41-06769 |  |  | Resolved
11 |  | A367-040-81-41-06770 |  |  | Resolved
12 |  | A367-040-81-41-06771 |  |  | Resolved
13 |  | A367-040-81-41-06772 |  |  | Resolved
14 |  | A367-040-81-41-06773 |  |  | Resolved
15 |  | A367-040-16-48-06775 |  |  | Resolved
16 | Area-16 | A367-040-16-48-00776 | 7 Foundation got hold by NFC CIVIL Dept(on fouling with some structure) |  | Pipe Rack & Pipe Bridge - 7 Foundation HOLD released by NFC. Foundations casting pending.
17 |  | A367-040-16-48-00777
18 |  | A367-040-16-48-00778
19 |  | A367-040-81-41-06779
20 |  | A367-040-81-41-06787; R-1
20 |  | A367-040-81-41-06789 | Revised bridge drawing required. |  | Resolved, Drg. Received on 22-12-2020
21 |  | A367-040-81-41-06786; R-1 | Due to the above reason detail engg not done for this bridge super structure too in co-relation with the pipe rack super structure. So EIL shall confirm the latest revision. |  | Detail Engg is under progress from TPL end.
22 |  | A367-040-81-41-06787; R-1
23 |  | A367-040-81-41-06788; R-2
24 |  | A367-040-81-41-06790; R-0
25 | Area-24 | A367-040-81-41-06705 | Bridge drg 06705 issued on 25.08.20 by EIL, but drg not received from NFC. |  | Resolved, Drg. Received on 1-1-2021
26 | Area-25 | A367-040-81-41-06791_Rev-0 | 1. Regarding Area-25 pipe rack structure crossing the Overhead electrical transmission line. So the design drawing may change. Due to this reason detail engineering not done. 2. TPL Engg comments: Table-1 does not include Tier-1 & Tier-2 levels. Please confirm levels marked in elevation can be followed or not. As per Table-1 no of cable trays are 2, however section 1-1, cable tray marked are 6. Please confirm. 3. TPL Engg comments: Table-1 does not include Tier-1 & Tier-2 levels. Please confirm levels marked in elevation can be followed or not. As per Table-1 no of cable trays are 2, however section 1-1, cable tray marked are 6. Please confirm. |  | Site Revised foundation Drawings shared by NFC on Jul'21, So progress effected. Moreover, the progress affected due to the High Tension Overhead Transmission Lines above the foundations. In addition to the above the PR24 to PR25 road crossing bridge affected due to the OHT line.
27 |  | A367-040-81-41-06792_Rev-0
28 |  | A367-040-81-41-06793_Rev-0
29 |  | A367-040-81-41-06794_Rev-0
30 |  | A367-040-81-41-06795_Rev-0
31 |  | A367-040-81-41-06796_Rev-0
32 |  | A367-040-81-41-06797_Rev-0
33 |  | A367-040-81-41-06798_Rev-0
34 | For instance, Area-4 | A367-040-16-48-00717; R-2 | Query on Pipe Rack drawing with respect to Piping GA drawing: In some of the pipe rack area piping GA drawing some pipes are shown in the Cantilever support at outside of the column in same elevation of Tier-1 and some intermediate beams are provided in between the Tier-1 & Tier-2 in the portion of the bridge area for supporting the pipes during crossover. But the same is not shown in the pipe rack design drawings & Bridge Tower section view. | Like this many other Area piping GAD drgs are also having these type of comments. Need to be clarified at the earliest, because we already in the stage of completing the detail engineering w.r.t. the design drawing of super structure & also started to supply the fabricated structure. Comment intimated date: 29/09/2020 | Resolved, Typical Drg. Received on 4-1-2021 which is applicable for necessary area of pipe rack.
35 |  | A367-040-16-48-00718; R-2
36 |  | A367-040-81-41-06719; R-2
37 |  | A367-040-81-41-06720_Rev-1
38 |  | A367-040-81-41-06721_Rev-1
Note: | 1. The above points may increase based on the inputs & subsequent detail engg stage.
Additional Points w.r.t. the further detail engg. Subsequent to the receipt of Revised drawings.
Sl.No. | Area No. | Drawing No. | Observations | Remarks | STATUS
1 | Area-24 | A367-040-81-41-06803; R-1 | Plan elevation of Grid 13 & 14 is not matching with Grid 1-36 & 1-37. | Commented drawing enclosed. | Revised Drawings shared by NFC on 19 Feb'21, Erection work in progress by TPL. Some foundations are pending due to live cable on the particular foundation area.
2 |  | A367-040-81-41-06804; R-1 | In elevation drawing, the Grid 32 & 33 is additionally shown but the same is not shown in the plan drawings. | Commented drawing enclosed.
3 |  | A367-040-81-41-06801; R-2
4 |  | A367-040-81-41-06802 & 06803; R-1
1 | Area-14 | A367-040-16-48-00766 | Revised Drawings received on Mar-21 |  | After Detail Engineering, the fabricated structure was supplied to site. After that the PR14 civil GAD & elevation was revised by NFC-Civil at SEP'21. Due to that there is huge involvement of structure modification work at site, so that the quantum of modification need to be made jointly for the additional work, progress is delayed due to this.
2 |  | A367-040-16-48-00767
3 |  | A367-040-16-48-00768
4 |  | A367-040-16-41-00769
5 |  | A367-040-16-41-00770
6 |  | A367-040-16-41-00771
7 |  | A367-040-16-41-00772
8 |  | A367-040-16-41-00773
9 |  | A367-040-16-48-00775

## Piping Constraint
List of Piping work related RFI pending from EIL/NFC - As on date 10-Oct-2021
Sl.No. | Area No. | Drawing No. | Observations | Remarks | As on date Status
1 | General | SOQ/SOR & Piping GAD | There is no supply item of 2" full coupling (Galv) SCRF in the SOQ/SOR w.r.t. the Galv SCRM pipes in SOQ/SOR - Need to be resolved at the earliest. | Intimated through email by 28-Oct-20 & reminder on 21-Nov-20. | As discussed with NFC on 17.03.21 TPL has to make SOQ missing Item list and submission for approval. The same is under progress.
2 |  |  | There is no supply item of 4" full coupling (Galv) SCRF in the SOQ/SOR w.r.t. the Galv SCRM pipes in SOQ/SOR - Need to be resolved at the earliest.
3 |  |  | There is no supply item of 6" full coupling (Galv) SCRF in the SOQ/SOR w.r.t. the Galv SCRM pipes in SOQ/SOR - Need to be resolved at the earliest.
4 |  |  | There is no supply item for 3" SOFF Flange (rubber lined), w.r.t. the supply items for rubber lined pipes with plain end & supply item for rubber lined 90deg elbow with Bevel end. The execution methodology for rubber line piping shall be, we will procure bare pipe & bare elbow, spools will be fabricated with flange welded on both ends, rubber lining shall be done on spools, spools will be erected & connected through flange bolting - Need to be resolved at the earliest.
5 |  |  | Wherever the RW & FW encounters underground road/ramp crossing occurs - hume pipes/RCC trenches/pipe culverts front required as applicable in drawings from Plants & Non-Plants - Need to be resolved at the earliest. | Intimating in the Daily Progress Report.
6 |  |  | Wherever the utility/process piping encounters underground road/ramp crossing occurs - hume pipes/RCC trenches/pipe culverts front required as applicable in drawings from Plants & Non-Plants - Need to be resolved at the earliest.
7 |  |  | Service wise, Size wise & MOC wise pipe support details on the pipe rack need to be provided by EIL/NFC. In piping GAD drawing the same is not shown. - Received , BOM need to be made.
8 | Area-4 | A367-000-16-43-0041_Rev-2 | The pipeline 25-NG-041-1503-A21A is shown in Area-1 to 3 piping GAD (A367-000-16-43-0011_Rev-1 ; A367-000-16-43-0021_Rev-0; A367-000-16-43-0031_Rev-0) but the same is not shown in the Area-4&5 drawing, but the same is shown again in Area-6 piping GAD (A367-000-16-43-0061_Rev-1) - Need to be resolved at the earliest. | Observed while reviewing the piping GAD drawings. | Still Pending from NFC/EIL
9 | Area-5 | A367-000-16-43-0051_Rev-1
10 | Area-5 | A367-000-16-43-0051_Rev-1 | In the Area-5 piping GAD there are 14 pipelines shown, whereas in the Area-6 piping GAD there is 16 pipelines shown that too in the shuffled manner - Need to be resolved at the earliest.
11 | Area-6 | A367-000-16-43-0061_Rev-1
12 | Area-6 | A367-000-16-43-0061_Rev-1 | In Area-6 Piping GAD drawing sheet-2 of 2 is not available. Moreover, 6-47 & 48 column shown in piping GAD but the same is not shown in corresponding Area-6 pipe rack structural drawing - Need to be resolved at the earliest.
Note: | 1. This shall not to be considered as the final RFI list related to piping work, the RFI shall increase based on the detail engineering.

## Hindrance Register
340092 Piping Project
S.No | Date | Reason for stoppage | Progress Effected no.of Hours | Remarks
1 | 2021-03-01 | Work stopped NFC site because of 1 workmen death at NPCIL site | 24 Hrs
2 | 2021-03-01 | Area-13,14,23 & 24 Drawing Approval pending from NFC |  | Cleared on 13-03-21
3 | 2021-03-01 | Area-06 Bridge Erection Hold from NFC |  | Cleared on 15-03-21
4 | 2021-03-15 | Area-15(7 Foundations) , 16(7 foundations) Drawing Hold from NFC
5 | 2021-04-01 | Vendor Approval for Fuel Dispensing Unit |  | Cleared on
6 | 2021-04-01 | Breathing Air Bullet platform and drawings confirmation to Proceed
7 | 2021-04-01 | Diesel Storage Tanks Drawings Approval
8 | 2021-04-01 | Diesel Storage Tanks Input requirment for Peso Approval
9 | 2021-04-01 | Ammonia Cracker P&ID and QA Approval
10 | 2021-04-01 | Rubber Lined items isometric drawing review and approval confirmation on NON-SOQ Items
11 | 2021-04-01 | Specifications and painting confirmation for handrail, Gratings, Ladder and Chequered Plate
12 | 2021-04-01 | Confirmation and Drawings for water Service, Valve SOQ in civil Structure
13 | 2021-04-01 | Confirmation on Valve Technical Clarification
14 | 2021-04-01 | Raw Water pipe line - Non SOQ quantity & items need to be confirmed.
15 | 2021-04-01 | Pipe Trench required for Underground piping (road crossings & PFFF area).
16 | 2021-04-11 | Progress Affected due to Powershutdown on 11-Apr-2021 | Half Day
17 | 2021-04-12 | Progress Affected due to Powershutdown on 12-Apr-2021 | Full Day
18 | 2021-04-28 | Progress Affected due to Powershutdown on 28-Apr-2021 | Half Day
19 | 2021-04-30 | Breathing Air Bullet 11 no's arrived at site foundations required to erect the same ASAP
20 | 13/5/2021 | Progress Affected due to Powershutdown on 12-May-2021 (AREA-11) | 8 HRS
21 | 22/5/2021 | Progress Affected because of heavy showers (18.00-19.30) | 1.5 hrs
22 | 2021-05-28 | Progress Affected because of heavy showers(19.15 - 22.00) | 3.75hrs
23 | 2021-06-02 | Progress Affected because of heavy showers(18.00 - 19.30) | 1.5hrs
24 | 2021-06-07 | Progress Affected Due to Power cut | 30 min
25 | 2021-06-17 | Progress Affected because of heavy showers(12.30 - 13.10) | 40 min
26 | 2021-06-18 | Progress Affected because of heavy showers(19.30 - 20.20) | 50 min
27 | 2021-05-19 | Progress Affected because of Power shutdown(9.54 - 10.17) | 23 min
28 | 2021-06-21 | Progress Affected because of heavy showers(15.55 - 16.45) | 50 min
29 | 2021-06-21 | Progress Affected because of heavy showers(17.03 - 18.15) | 1hr 12min
30 | 2021-06-22 | Progress Affected because of heavy showers(18.20 - 19.00) | 40 min
31 | 2021-06-23 | Progress Affected because of heavy showers(14.35 - 15.50) | 1hr 15min
32 | 2021-06-23 | Progress Affected because of Power shutdown(16.20 - 17.20) | 1hr
33 | 2021-06-23 | Progress Affected because of heavy showers(17.20 - 17.45) | 25 min
34 | 2021-06-23 | Progress Affected because of Power shutdown(19.10 - 19.50) | 40 min
35 | 2021-06-25 | Progress Affected because of Power shutdown(9.37 - 10.30) | 1hr7min | area 11
36 | 2021-06-29 | Progress Affected because of Power shutdown(multiple) | 2hr45min
37 | 2021-07-12 | Progress Affected because of heavy showers(19.20 - 19.30) | 10 MIN
38 | 2021-07-13 | Progress Affected because of heavy showers(17.00 - 17.50) | 50 MIN
39 | 2021-07-14 | Progress Affected because of DRIZZLE(13.50 - 14.10) | 20 MIN
40 | 2021-07-17 | Progress Affected because of heavy showers(11.42 - 12.30) | 38 MIN
41 | 2021-07-26 | Progress Affected because of heavy showers(7.00 - 20.00) | 13 hrs
42 | 2021-07-27 | Progress Affected because of heavy showers(12.00 - 13.00) | 1 HR
43 | 2021-07-30 | Progress Affected because of heavy showers(16.15 - 16.40) | 25 MIN
44 | 2021-07-31 | Progress Affected because of heavy showers(08.00 - 9.30) | 1HR.30MIN
45 | 2021-07-31 | Progress Affected because of heavy showers(15.00 - 16.00) | 1HR
46 | 2021-07-31 | Progress Affected because of heavy showers(12.45 - 14.40) | 1HR 55MIN
47 | 2021-08-02 | Progress Affected because of heavy showers(8.00 - 09.40) | 1hr 40min
48 | 2021-08-02 | Progress Affected because of heavy showers(15.00 - 16.00) | 1hr
49 | 2021-08-02 | Progress Affected because of heavy showers(17.00 - 22.00) | 6hr
50 | 2021-08-03 | Progress Affected because of heavy showers(6.00 - 10.30) | 4hr 30min
51 | 2021-08-03 | Progress Affected because of heavy showers(12.00 - 23.59) | 11hr 59min
52 | 2021-08-04 | Progress Affected because of heavy showers(00.00 - 10.30) | 10HR 30MIN
53 | 2021-08-04 | Progress Affected because of heavy showers(13.30 - 23.59) | 10HR 29MIN
54 | 2021-08-05 | Progress Affected because of heavy showers(11.45 - 14.00) | 2hr15min | ALTHOUGH HEAVY SHOWERS ARE STIPULATED BUT DRIZZLE WAS CONTINOUS
55 | 2021-08-05 | Progress Affected because of heavy showers(18.30 - 19.00) | 30min
56 | 2021-08-05 | Progress Affected because of heavy showers(19.10 - 19.25) | 15min
57 | 2021-08-05 | Progress Affected because of heavy showers(19.35 - 19.55) | 20min
55 | 2021-08-06 | Progress Affected because of heavy showers(9.25 - 10.00) | 35MIN
56 | 2021-08-06 | Progress Affected because of heavy showers(11.45 - 20.00) | 8HR15MIN
57 | 2021-08-20 | Progress Affected because of heavy showers(14.40 - 15.30) | 50min
58 | 2021-08-25 | Progress affected because of powder Shutdown(5:30 - 7:00PM) | 2 HOUR
59 | 2021-09-03 | progress affected because of power Tripped (9:20 -11:15AM) | 2HOUR
60 | 2021-09-09 | Progress affected because of power Tripped (3:45- 4:20) | 40 MIN
61 | 2021-09-11 | progress affected because of power Shut Down (12:00- 2:00) | 2 HOUR
62 | 2021-09-13 | progress affected because of power tripped (11:15 - 2:50) | 2 HOURS
63 | 2021-09-14 | progress affected because of Tripped (2:20 - 6:15 ) | 4 HOUR
64 | 2021-09-15 | progress affected because of power tripped (10:30AM - 4:30PM) | 6 HOUR
65 | 2021-09-20 | progress affected because of power tripped (2:00 -2:20) | 20MIN
66 | 2021-09-21 | progress affected because of power Tripped( CSS01) (4:30- 4:50) | 20MIN
67 | 2021-09-22 | progress affected because of power tripped ( CSS 01 & CSS 03)(11:30 - 12:50) | 2 HOUR
68 | 2021-09-25 | Progress affected because of power tripped (CSS01) | 20Min
69 | 2021-09-28 | Progress affected because of power tripped (CSS01) (10:45- 11:06) | 25MIN
70 | 2021-09-29 | progress affected because of power tripped (CSS03) (11AM-12:30PM) | 1:30Min
71 | 2021-10-13 | Progress affected because of power cut in Tripped fabrication Yard (20min) | 20Min
72 | 2021-10-15 | Less progress Due to Duserra Festival | 1 DAY

## Summary
| PIPING | [5 empty] | PIPE RACK STRUCTURE | [5 empty] | TOTAL MANPOWER
| Pipes supply (mtr) | blasting (mtrs) | painting (mtrs) | Fit up(id) | Welding(id) | placing(IM) | Structural Supply (MT) |  | Erection(MT) |  | Alignment (MT) | Welding (MT) | STAFF | LABOUR
SCOPE | 107231 | 75182 | 75182 | 123470 | 123470 | 489572 | 4400 |  | 4400 |  | 4400 | 4400
PLANNED (AUG) | 5000 | 6000 | 6000 | 10000 | 10000 | 40000 | 400 |  | 500 |  | 400 | 400 | 58 | 272
Today (21-08-2021) | 0 | 0 | 0 | 78 | 274 | 1728 | 0 |  | 10 |  | 7 | 12
Cumulative- August | 0 | 3066.93 | 3066.93 | 7652 | 7696.5 | 37169.88 | 0 |  | 189.6 |  | 249.7 | 576.7 | 330
Total (up to date) | 95680 | 52561.93 | 52561.93 | 29674 | 29718.5 | 183767.88 | 3383 |  | 2349.7 |  | 1707.5 | 2374.4
Manpower Strength | STAFF | 14 | LABOUR | 149 |  |  | STAFF | 27 | LABOUR | 111
| INDUCTION (NEW) | [5 empty] | 0